## Sheet1
Senior Project - Spring / Summer 2015
For week ending 05/17/15
Name: Dylan Holliday
Project: Career Services
| Date | Time - From/To | Hours | Worked On
| 2015-05-15 | 8:00am-12:00pm | 4 | Working on html submission site
| 2015-05-15 | 12:00pm-2:30pm | 2.5 | Researching PHP Security
| 2015-05-17 | 2:00pm-6:00pm | 4 | Working on html submission site
Total 10.5

## Sheet2
Senior Project - Spring / Summer 2015
For week ending 5/17/15
Name: Kyle Johnson
Project: Career Services
| Date | Time - From/To | Hours | Worked On
| 05/11/2015 Mon | 12:30pm-3:30pm | 3 | Minor Changes to GUI, Code Review, Class Meeting, Team Meeting
| 05/14/2015 Thu | 5:45pm-9:45pm | 4 | Search Box Formatting, Hash Function, Additional GUI Work, Code Cleanup
| 05/15/2015 Fri | 12:00pm-5:15pm | 5.25 | Fix Commit Conflict, Implement Database Functionality to GUI
Total 12.25

## Sheet3
Senior Project - Spring / Summer 2015
For week ending 5/17/15____________________________
Name_______________________________________________________ | Kevin Reynolds
Project ______________________________________________________ | Career Services
| Date | Time - From/To | Hours | Worked On
| 2015-05-11 | 2:00pm-3:00pm | 1 | Class Meeting
| 2015-05-12 | 6:00pm-7:00pm | 1 | Import MySQL database
| 2015-05-14 | 4:00pm-10:30pm | 6.5 | From Excel to online database
| 2015-05-15 | 1:00pm-5:00pm | 4 | Code for modification of database
| 2015-05-17 | 2:00pm-3:00pm | 1 | Reformat Import for Schema
Total 13.5

## Sheet4
Senior Project - Spring / Summer 2015
For week ending _________5/17/2015_________
Name_______________________________________________________ |  | Zhenyu Xia
Project ______________________________________________________ |  | Job Fair
| Date | Time - From/To | Hours | Worked On
| 2015-05-11 | 2:00:3:30pm | 1.5 | Meetings, class
| 2015-05-13 | 2:30:5:00pm | 2.5 | Make databases, updates to database, changes
| 2015-05-14 | 3:00:4:00pm | 1 | Analyzing database and alternative methods
| 2015-05-15 | 1:00:5:15pm | 4.25 | Create database, code, meeting
| 2015-05-16 | 3:00:4:30pm | 1.5 | Analyzing different database solutions
| 2015-05-17 | 12:30:1:30pm | 1 | Working on visual studio c#
Total 11.75