## Sheet1
Senior Project - Spring / Summer 2015
For week ending 04/26/15
Name: Dylan Holliday
Project: Career Services
| Date | Time - From/To | Hours | Worked On
| 2015-04-17 | 1:00-2:30pm | 1.5 | Client/group meeting
| 2015-04-19 | 3:00-5:00pm | 2 | Researching qr codes
| 2015-04-21 | 9:30-10am | 0.5 | Talking to Stu about card scanner
| 2015-04-21 | 1:00-1:30pm | 0.5 | Learning about ID cards in Tawanka
| 2015-04-21 | 5:00-7:00pm | 2 | Researching programmable usb magnetic card reader
| 2015-04-22 | 1:00-3:00pm | 2 | Researching/setting up databases
| 2015-04-22 | 3:00-4:30pm | 1.5 | Client meeting
Total 10

## Sheet2
Senior Project - Spring / Summer 2015
For week ending 4/26/15
Name: Kyle Johnson
Project: Career Services
| Date | Time - From/To | Hours | Worked On
| 04/15/2015 Wed | 2:00pm – 3:00pm | 1 | Class and first meeting; email Shannon
| 04/16/2015 Thu | 12:30pm-2:00pm | 1.5 | Start the SRS document, add basic template and information
| 04/17/2015 Fri | 1:00pm-2:00pm | 1 | First meeting with Shannon, team discussion
|  | 9:45pm-10:00pm | 0.25 | Google Hangout Set Up
| 04/20/2015 Mon | 10:00am-11:00am | 1 | QR Code Research
|  | 1:30pm-3:45pm | 2.25 | Class meeting. Team meeting: Pivotal Tracker and prioritizing
|  | 7:45pm-10:00pm | 2.25 | Set up GitHub, work on SRS Document
| 04/22/2015 Wed | 1:00pm-4:45pm | 3.75 | Team Meeting: SRS Document, more planning, barcode scanner research. Meet with Shannon.
Total 13

## Sheet3
Senior Project - Spring / Summer 2015
For week ending 4/26/15
Name_______________________________________________________ | Kevin Reynolds
Project ______________________________________________________ | Career Services
| Date | Time - From/To | Hours | Worked On
| 2015-04-20 | 2:00pm-3:00pm | 1 | Class Meeting
| 2015-04-22 | 1:00pm-4:30pm | 3.5 | SRS and met with Shannon
| 2015-04-24 | 7:30pm-9:30pm | 2 | Hooking up printer and getting it to run with C# code
| 2015-04-26 | 7:00pm-9:00pm | 2 | Worked on importing from Excel
Total 8.5

## Sheet4
Senior Project - Spring / Summer 2015
For week ending 4/26/2015
Name_______________________________________________________ |  | Zhenyu Xia
Project ______________________________________________________ |  | Career Services
| Date | Time - From/To | Hours | Worked On
| 2015-04-15 | 3:00/4:00pm | 1 | Meeting with the group and class
| 2015-04-16 | 4:00/5:00pm | 1 | Research questions to ask and research the SRS
| 2015-04-17 | 11:00/12:00am | 1 | Research questions to ask and research/work on SRS
| 2015-04-17 | 1:00/2:00pm | 1 | Meeting with the group and customer Shannon
| 2015-04-17 | 8:00/9:00pm | 1 | Working and researching tasks
| 2015-04-18 | 6:00/7:00pm | 1 | Research and SRS
| 2015-04-20 | 2:00/4:00pm | 2 | Meeting
| 2015-04-22 | 1:00/4:30pm | 3.5 | Meetings
Total 11.5